**Coomera to Helensvale Duplication**

Night works – electrification and power systems

July-September 2017

As part of the Coomera to Helensvale Duplication, Queensland Rail is installing overhead electrification lines and rail power systems, between Coomera and Helensvale stations, on **selected nights from late July until early September**, weather and operational factors permitting.

The work requires the use of heavy machinery including trucks, cranes and lifts to run overhead electrical wire between mast foundations and conduct overhead modifications. For safety and in order to maintain train services during the day, these works must be undertaken at night.

**Scheduled night works**

|  |  |  |
| --- | --- | --- |
| **Location** | **Dates and hours of work** | **Type of work** |
| Rail corridor between Coomera station and Coomera River | **10pm to 5am** the next morning on:   * **Sunday 30 July to Thursday 3 August** (over 5 nights) | * Installing power supply for signalling systems * Installing overhead electrification lines for the new track * Use of construction machinery and vehicles, with reversing beepers and flashing lights * Use of mobile lighting towers. |
| Rail corridor between Gold Coast Highway, Helensvale and Helensvale station | **10pm to 5am** the next morning on:   * **Sunday 6 to Thursday 10 August** (over 5 nights) * **Sunday 13 to Thursday 17 August** (over 5 nights) |
| Rail corridor between Ridgevale Drive, Helensvale and Helensvale station | **8pm to 5am** the next morning on:   * **Sunday 20 to Thursday 24 August** (over 5 nights) |
| Rail corridor between Coomera station and Ford Road, Coomera | **10pm to 5am** the next morning on:   * **Sunday 27 to Thursday 31 August** (over 5 nights) * **Sunday 17 to Thursday 21 September** (over 5 nights) |
| Rail corridor between Coomera station and Helensvale station | **10pm to 5am** the next morning on:   * **Sunday 24 to Thursday 28 September** (over 5 nights) |
| Residents located near the rail corridor in these areas may experience increased noise and may also be impacted by the use of lighting associated with this activity. Every effort will be made to carry out these works with minimal disruption.  Queensland Rail apologises for any inconvenience caused and appreciates the local community’s cooperation during these important works. | | |

For more information about this project please phone **1800 664 484** (during construction hours), email **C2H@qr.com.au** or visit **queenslandrail.com.au/C2H**