

**Boondall station accessibility upgrade**

**PROJECT UPDATE – JULY 2019**

**Queensland Rail’s Boondall station accessibility upgrade is part of the program to upgrade stations across the South East Queensland network, making them accessible for all customers.**

**Project progress**

Activities undertaken recently at Boondall have included:

* construction of lift shafts to platform level – platforms 1 and 2
* concrete pours for lift wells – platforms 1 and 2
* prepare footings and landings – Aberdeen Parade, platform 2
* platform 1 roof structure
* installation of new footbridge and stairs (pictured).

**Upcoming works**

In the coming weeks, customers and the community can expect to see the following activities:

* installation of platform 2 stairs
* installation of pre-cast lift shafts
* electrical upgrade
* platform raising.

The station will be closed for uninterrupted works from 11.30pm Friday 2 until 4am Monday 5 August. Rail services will not stop at Boondall during this time. Half-hourly shuttle buses will take customers to North Boondall to connect with inbound and outbound services (allow an additional 30 minutes’ travel time).





# Construction impacts

# Normal working hours are 6am to 5pm Monday to Saturday. Construction activities may involve:

# noise associated with heavy machinery

# temporary changes to station access paths

# changed traffic/parking conditions (Aberdeen Parade)

# increased vehicle movements near works

# mobile lighting towers for night works.

# Please take care around the work zones.

# Local residents will be given advance notification of construction activities likely to cause impacts, including after hours work (nights and Sundays, as required).

# We thank customers and the community for your patience and cooperation as we work to improve your station.

# Contact us

# For more information or to provide feedback:

# Phone: 1800 722 203 (free call)

# Email: stationsupgrade@qr.com.au

# Website: queenslandrail.com.au

