## North Coast Line
Regional Operations: NCL Possession Calendar 19/05/2026 - 19/05/2028
Brisbane System: Tamaree to Parana, Townsville System: North Coast Line - Rockhampton to Cairns.
Pb Number | Start Date | End Date | Work Types | Traffic Comments | Possession Territory
PB202311-01865 | Civil: 01. Sat 23/05/2026 09:00 | Civil: 01. Thu 28/05/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202311-01376 | Civil: 01. Sat 23/05/2026 14:00 | Civil: 01. Thu 28/05/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Thu Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Thu Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Thu Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Thu All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202511-00655 | Civil: 01. Sat 23/05/2026 14:40 | Civil: 01. Thu 28/05/2026 14:00 | General Mtce | TOTAL TRACK CLOSURE - The Caves - Yaamba | Townsville Track Possessions
PB202503-00744 | Civil: 01. Sat 23/05/2026 20:00 | Civil: 01. Thu 28/05/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 DAYS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Thu Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Thu Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Thu Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202509-01705 | Civil: 01. Sun 24/05/2026 00:01 | Civil: 01. Thu 28/05/2026 20:00 | Culvert Renewal | TOTAL TRACK CLOSURE - NOME - PARTINGTON (UP/DOWN ROAD) NCL SHUTDOWN Note: Times have been updated. Previously 06:00 Sun 24/05/2026 - 20:00 Thu 28/05/2026 | Townsville Track Possessions
PB202503-00745 | Civil: 01. Sun 24/05/2026 02:00 | Civil: 01. Fri 29/05/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Fri Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Fri Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Fri Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00241 | Civil: 01. Sun 24/05/2026 05:00 | Civil: 01. Thu 28/05/2026 20:00 | Bridge Mtce | TOTAL TRACK CLOSURE - MACKAY - EARAKALA Note: Times have been updated. Previously 22:30 Sat 23/05/2026 - 20:00 Thu 28/05/2026 | Townsville Track Possessions
PB202604-01288 | Civil: 01. Sun 24/05/2026 05:00 | Civil: 01. Tue 26/05/2026 18:00 | Project | TOTAL TRACK CLOSURE - WAUGH TO BABINDA NCL SHUTDOWN | Townsville Track Possessions
PB202510-01128 | Civil: 01. Sun 24/05/2026 05:30 | Civil: 01. Fri 29/05/2026 14:00 | Re-conditioning | TOTAL TRACK CLOSURE ALOOMBA - GORDONVALE | Townsville Track Possessions
PB202603-00246 | Civil: 01. Sun 24/05/2026 05:40 | Civil: 01. Thu 28/05/2026 07:00 | NCL Shutdown Signals-generic | TOTAL TRACK CLOSURE ROSELLA - MACKAY SECTION - 1 Road / Third Road not available for stowing - Max 2 trains to be stowed at MKY (restricted to 686m if stowing in QR Roads) | Townsville Track Possessions
PB202510-00987 | Civil: 01. Sun 24/05/2026 06:00 | Civil: 01. Thu 28/05/2026 07:00 | Formation | TOTAL TRACK CLOSURE - CALEN TO YALBAROO NCL REGIONAL SHUTDOWN Note: Times have been updated. Previously 06:00 Sun 24/05/2026 - 18:00 Wed 27/05/2026 | Townsville Track Possessions
PB202511-01288 | Civil: 01. Sun 24/05/2026 06:00 | Civil: 01. Thu 28/05/2026 08:00 | Level Crossing | TOTAL TRACK CLOSURE - Yaamba - Glen Geddes Note: Times have been updated. Previously 06:00 Sun 24/05/2026 - 20:00 Sun 24/05/2026 | Townsville Track Possessions
PB202601-01985 | Civil: 01. Sun 24/05/2026 06:00 | Civil: 01. Fri 29/05/2026 06:00 | Re-Sleepering | TOTAL TRACK CLOSURE (BABINDA YARD - DEERAL) | Townsville Track Possessions
PB202604-01269 | Civil: 01. Sun 24/05/2026 06:15 | Civil: 01. Thu 28/05/2026 08:00 | Project | TA - MAJOR (TOTAL TRACK CLOSURE) - OGMORE - ST LAWRENCE Note: Times have been updated. Previously 06:15 Sun 24/05/2026 - 18:00 Wed 27/05/2026 | Townsville Track Possessions
PB202302-00874 | Civil: 01. Sun 24/05/2026 06:20 | Civil: 01. Tue 26/05/2026 18:00 | Turnout Replace | TSV SUB TOTAL TRACK CLOSURE - THROUGH ROAD PARTINGTON YARD -Partington PI/Through Rd, to P8 closed from South End -No access into the South End of Partington Yard via Dn Rd/111B points -Dn Rd closed from Signal PN118 to PN 125 -Dead End Siding closed -Toll North Freight open -Sun Metals open -Copper Refinery open -Julago Cattle open -Access into Partington Yard from the North End only -P1 to P8 open from the North End only -Reduced stowage/storage capacity for P1 to P4 during closure times | Townsville Track Possessions
PB202603-00333 | Civil: 01. Sun 24/05/2026 06:20 | Civil: 01. Thu 28/05/2026 18:00 | Re-Sleepering | TOTAL TRACK CLOSURE - HOME HILL - AYR (BURDEKIN BRIDGE) REGIONAL SHUTDOWN | Townsville Track Possessions
PB202410-01779 | Civil: 01. Sun 24/05/2026 06:30 | Civil: 01. Thu 28/05/2026 06:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE SHUTDOWN (96HRS) & ISOLATION (TBC) AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK. NIL ELECTRICS | Townsville Track Possessions
PB202509-02105 | Civil: 01. Sun 24/05/2026 07:00 | Civil: 01. Fri 29/05/2026 07:00 | Project | TOTAL TRACK CLOSURE **INNISFAIL - WAUGH - BABINDA** NCL SHUTDOWN | Townsville Track Possessions
PB202603-00182 | Civil: 01. Sun 24/05/2026 07:00 | Civil: 01. Thu 28/05/2026 08:00 | NCL Shutdown Signals-generic | TOTAL TRACK CLOSURE KOUMALA - YUKAN SECTION | Townsville Track Possessions
PB202602-00630 | Civil: 01. Sun 24/05/2026 07:20 | Civil: 01. Thu 28/05/2026 07:20 | Level Crossing | TOTAL TRACK CLOSURE SARINA - DAWLISH SECTION Note: Times have been updated. Previously 07:30 Mon 25/05/2026 - 20:30 Tue 26/05/2026 | Townsville Track Possessions
PB202503-00747 | Civil: 01. Sun 24/05/2026 09:00 | Civil: 01. Fri 29/05/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days ALIGNED TO SEQ NCL SCAS Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202604-00254 | Civil: 01. Sun 24/05/2026 15:30 | Civil: 01. Thu 28/05/2026 18:00 | Level Crossing | TOTAL TRACK CLOSURE - MOOKARA TO BOWEN JUNCTION NCL SHUTDOWN | Townsville Track Possessions
PB202604-00591 | Civil: 01. Tue 26/05/2026 08:00 | Civil: 01. Wed 27/05/2026 14:00 | OHLE-generic | TOTAL TRACK CLOSURE - Theebine - Tamaree | Brisbane Track Possessions
PB202603-00625 | Civil: 01. Sun 31/05/2026 07:00 | Civil: 01. Sun 31/05/2026 08:30 | Rail Drop | TOTAL TRACK CLOSURE - RED ROAD JETTY | Townsville Track Possessions
PB202604-01728 | Civil: 01. Sun 31/05/2026 13:00 02. Mon 01/06/2026 06:00 | Civil: 01. Sun 31/05/2026 19:00 02. Mon 01/06/2026 18:00 | Project | TA - MAJOR (TOTAL TRACK CLOSURE) - OGMORE - ST LAWRENCE | Townsville Track Possessions
PB202604-00751 | Civil: 01. Mon 01/06/2026 09:15 Isolation: 01. Mon 01/06/2026 09:00 | Civil: 01. Mon 01/06/2026 16:00 Isolation: 01. Mon 01/06/2026 16:00 | GIJ's | TOTAL TRACK CLOSURE - ISOLATION - Iveragh - Benaraby | Brisbane Track Possessions
PB202604-01182 | Civil: 01. Mon 01/06/2026 10:25 | Civil: 01. Mon 01/06/2026 15:20 | General Mtce | TOTAL TRACK CLOSURE - Elliott - Bundaberg | Brisbane Track Possessions
PB202604-01245 | Civil: 01. Mon 01/06/2026 11:30 Isolation: 01. Mon 01/06/2026 11:15 | Civil: 01. Mon 01/06/2026 14:30 Isolation: 01. Mon 01/06/2026 14:30 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Mungar - Maryborough West | Brisbane Track Possessions
PB202603-01269 | Civil: 01. Tue 02/06/2026 06:20 | Civil: 01. Tue 02/06/2026 15:00 | General Mtce | TOTAL TRACK CLOSURE Boogan - Mundoo | Townsville Track Possessions
PB202604-01250 | Civil: 01. Wed 03/06/2026 11:00 Isolation: 01. Wed 03/06/2026 10:45 | Civil: 01. Wed 03/06/2026 14:30 Isolation: 01. Wed 03/06/2026 15:00 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Kinkuna - Bundaberg | Brisbane Track Possessions
PB202603-01020 | Civil: 01. Thu 04/06/2026 05:00 02. Fri 05/06/2026 19:00 03. Sat 06/06/2026 17:00 04. Sun 07/06/2026 17:00 05. Mon 08/06/2026 19:00 06. Tue 09/06/2026 19:00 07. Wed 10/06/2026 19:00 08. Thu 11/06/2026 19:00 | Civil: 01. Thu 04/06/2026 14:00 02. Sat 06/06/2026 02:00 03. Sun 07/06/2026 02:00 04. Sun 07/06/2026 23:00 05. Tue 09/06/2026 05:00 06. Wed 10/06/2026 02:00 07. Thu 11/06/2026 02:00 08. Fri 12/06/2026 01:00 | Re-Sleepering | TOTAL TRACK CLOSURE BABINDA - DEERAL | Townsville Track Possessions
PB202604-01729 | Civil: 01. Sun 07/06/2026 12:00 02. Mon 08/06/2026 06:00 | Civil: 01. Sun 07/06/2026 18:00 02. Mon 08/06/2026 18:00 | Project | TA - MAJOR (TOTAL TRACK CLOSURE) - OGMORE - ST LAWRENCE | Townsville Track Possessions
PB202605-00294 | Civil: 01. Mon 08/06/2026 07:00 | Civil: 01. Mon 08/06/2026 11:30 | General Mtce | TOTAL TRACK CLOSURE - Theebine - Paterson | Brisbane Track Possessions
PB202604-01549 | Civil: 01. Mon 08/06/2026 07:45 Isolation: 01. Mon 08/06/2026 07:30 | Civil: 01. Mon 08/06/2026 11:40 Isolation: 01. Mon 08/06/2026 11:40 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Theebine - Curra Section | Brisbane Track Possessions
PB202604-01186 | Civil: 01. Mon 08/06/2026 10:30 | Civil: 01. Mon 08/06/2026 15:30 | General Mtce | TOTAL TRACK CLOSURE - Berajondo- Baffle | Brisbane Track Possessions
PB202605-00878 | Civil: 01. Mon 08/06/2026 11:15 | Civil: 01. Mon 08/06/2026 13:15 | Turnout Mtce | TOTAL TRACK CLOSURE MERINDA - PRING SECTION | Townsville Track Possessions
PB202602-00343 | Civil: 01. Tue 09/06/2026 06:30 | Civil: 01. Fri 12/06/2026 18:00 | Re-Railing | TOTAL TRACK CLOSURE - TOWNSVILLE JETTY BLUE ROAD **FROM ARCHER STREET - CP TJ16** | Townsville Track Possessions
PB202602-00382 | Civil: 01. Tue 09/06/2026 06:30 | Civil: 01. Fri 12/06/2026 18:00 | Re-Railing | TOTAL TRACK CLOSURE - TOWNSVILLE JETTY BLUE ROAD **FROM ARCHER STREET - CP TJ16** | Townsville Track Possessions
PB202605-01258 | Civil: 01. Tue 09/06/2026 11:15 | Civil: 01. Tue 09/06/2026 18:00 | Turnout Mtce | TOTAL TRACK CLOSURE FORKLINE - TOWNSVILLE JETTY ALL ROADS | Townsville Track Possessions
PB202604-01242 | Civil: 01. Wed 10/06/2026 11:30 Isolation: 01. Wed 10/06/2026 11:15 | Civil: 01. Wed 10/06/2026 15:00 Isolation: 01. Wed 10/06/2026 15:00 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Maryborough West - Colton | Brisbane Track Possessions
PB202604-01730 | Civil: 01. Sun 14/06/2026 13:00 02. Mon 15/06/2026 06:00 | Civil: 01. Sun 14/06/2026 19:00 02. Mon 15/06/2026 18:00 | Project | TA - MAJOR (TOTAL TRACK CLOSURE) - OGMORE - ST LAWRENCE | Townsville Track Possessions
PB202601-01368 | Civil: 01. Mon 15/06/2026 01:30 02. Tue 16/06/2026 06:20 03. Wed 17/06/2026 06:20 04. Thu 18/06/2026 06:20 | Civil: 01. Mon 15/06/2026 18:00 02. Tue 16/06/2026 18:00 03. Wed 17/06/2026 18:00 04. Thu 18/06/2026 18:00 | Re-Railing | SUSPEND FOR NOMINATED TRAINS (CONN - CARDWELL) | Townsville Track Possessions
PB202604-01550 | Civil: 01. Mon 15/06/2026 07:45 Isolation: 01. Mon 15/06/2026 07:30 | Civil: 01. Mon 15/06/2026 11:40 Isolation: 01. Mon 15/06/2026 11:40 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Theebine - Curra Section | Brisbane Track Possessions
PB202604-01609 | Civil: 01. Mon 15/06/2026 10:30 | Civil: 01. Mon 15/06/2026 15:30 | General Mtce | TOTAL TRACK CLOSURE - Avondale - Littabella | Brisbane Track Possessions
PB202604-01179 | Civil: 01. Mon 15/06/2026 11:30 | Civil: 01. Mon 15/06/2026 15:00 | General Mtce | TOTAL TRACK CLOSURE - Howard - Wokka | Brisbane Track Possessions
PB202604-01199 | Civil: 01. Tue 16/06/2026 10:00 Isolation: 01. Tue 16/06/2026 10:20 | Civil: 01. Tue 16/06/2026 13:10 Isolation: 01. Tue 16/06/2026 14:30 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Irkanda - Baffle | Brisbane Track Possessions
PB202604-01711 | Civil: 01. Wed 17/06/2026 11:30 Isolation: 01. Wed 17/06/2026 10:45 | Civil: 01. Wed 17/06/2026 15:15 Isolation: 01. Wed 17/06/2026 16:00 | GIJ's ISOL REQ | TOTAL TRACK CLOSURE - ISOLATION - Howard - Wokka | Brisbane Track Possessions
PB202603-00988 | Civil: 01. Thu 18/06/2026 05:00 02. Fri 19/06/2026 19:00 03. Sat 20/06/2026 17:00 04. Sun 21/06/2026 17:00 05. Mon 22/06/2026 19:00 | Civil: 01. Thu 18/06/2026 14:00 02. Sat 20/06/2026 02:00 03. Sun 21/06/2026 02:00 04. Sun 21/06/2026 23:00 05. Tue 23/06/2026 05:00 | Re-Sleepering | TOTAL TRACK CLOSURE BABINDA - DEERAL | Townsville Track Possessions
PB202604-01200 | Civil: 01. Thu 18/06/2026 11:00 Isolation: 01. Thu 18/06/2026 10:20 | Civil: 01. Thu 18/06/2026 13:40 Isolation: 01. Thu 18/06/2026 14:00 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Baffle - Berajondo | Brisbane Track Possessions
PB202604-01566 | Civil: 01. Mon 22/06/2026 07:45 Isolation: 01. Mon 22/06/2026 07:00 | Civil: 01. Mon 22/06/2026 11:05 Isolation: 01. Mon 22/06/2026 11:05 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Curra - Paterson | Brisbane Track Possessions
PB202604-01202 | Civil: 01. Mon 22/06/2026 10:30 Isolation: 01. Mon 22/06/2026 09:45 | Civil: 01. Mon 22/06/2026 16:00 Isolation: 01. Mon 22/06/2026 16:00 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Baffle - Flinders | Brisbane Track Possessions
PB202604-01613 | Civil: 01. Mon 22/06/2026 10:15 | Civil: 01. Mon 22/06/2026 15:30 | General Mtce | TOTAL TRACK CLOSURE - Baffle - Irkanda | Brisbane Track Possessions
PB202510-00051 | Civil: 01. Tue 23/06/2026 05:00 | Civil: 01. Sat 27/06/2026 18:00 | Turnout Replace | TOTAL TRACK CLOSURE - TOWNSVILLE JETTY BLUE ROAD TJ101 - TIPPLER - TJ16 | Townsville Track Possessions
PB202602-00446 | Civil: 01. Tue 23/06/2026 06:00 | Civil: 01. Fri 26/06/2026 15:00 | BCM | TOTAL TRACK CLOSURE CLUDEN - FORKLINE **DOWN ROAD ONLY** | Townsville Track Possessions
PB202603-01200 | Civil: 01. Tue 23/06/2026 18:00 02. Wed 24/06/2026 18:00 03. Thu 25/06/2026 18:00 | Civil: 01. Wed 24/06/2026 02:30 02. Thu 25/06/2026 02:30 03. Fri 26/06/2026 01:00 | Re-Sleepering | TOTAL TRACK CLOSURE DEERAL - ALOOMBA | Townsville Track Possessions
PB202604-01171 | Civil: 01. Mon 29/06/2026 07:15 Isolation: 01. Mon 29/06/2026 07:00 | Civil: 01. Mon 29/06/2026 11:00 Isolation: 01. Mon 29/06/2026 11:00 | General Mtce | TOTAL TRACK CLOSURE - ISOLATION - Owanyilla Mungar | Brisbane Track Possessions
PB202603-00441 | Civil: 01. Mon 29/06/2026 08:40 | Civil: 01. Mon 29/06/2026 16:00 | Points | TOTAL TRACK CLOSURE - ISOLATION - NCL PARANA TO BENARABY | Brisbane Track Possessions
PB202604-01208 | Civil: 01. Mon 29/06/2026 09:30 Isolation: 01. Mon 29/06/2026 09:00 | Civil: 01. Mon 29/06/2026 15:00 Isolation: 01. Mon 29/06/2026 16:00 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Benaraby to Iveragh | Brisbane Track Possessions
PB202604-01190 | Civil: 01. Mon 29/06/2026 10:00 | Civil: 01. Mon 29/06/2026 15:00 | General Mtce | TOTAL TRACK CLOSURE - Bororen - Iveragh | Brisbane Track Possessions
PB202512-01013 | Civil: 01. Wed 01/07/2026 02:00 02. Thu 02/07/2026 05:00 03. Fri 03/07/2026 06:00 04. Sat 04/07/2026 06:00 | Civil: 01. Wed 01/07/2026 18:00 02. Thu 02/07/2026 18:00 03. Fri 03/07/2026 18:30 04. Sat 04/07/2026 18:00 | Relay-Rails General Mtce | TA MAJOR: TOTAL TRACK CLOSURE Conn to Hinchinbrook *** SUSPEND FOR TILT*** | Townsville Track Possessions
PB202603-01202 | Civil: 01. Thu 02/07/2026 18:00 02. Fri 03/07/2026 17:30 03. Sat 04/07/2026 18:00 04. Sun 05/07/2026 18:00 05. Mon 06/07/2026 17:30 06. Tue 07/07/2026 18:00 07. Wed 08/07/2026 19:00 08. Thu 09/07/2026 19:00 | Civil: 01. Fri 03/07/2026 03:00 02. Sat 04/07/2026 03:00 03. Sun 05/07/2026 03:00 04. Mon 06/07/2026 00:30 05. Tue 07/07/2026 03:00 06. Wed 08/07/2026 03:00 07. Thu 09/07/2026 03:00 08. Fri 10/07/2026 00:30 | Re-Sleepering | TOTAL TRACK CLOSURE KAMMA - PORTSMITH | Townsville Track Possessions
PB202501-01297 | Civil: 01. Fri 03/07/2026 05:00 02. Sat 04/07/2026 04:00 03. Sun 05/07/2026 06:00 04. Mon 06/07/2026 18:00 | Civil: 01. Fri 03/07/2026 14:00 02. Sat 04/07/2026 18:00 03. Sun 05/07/2026 18:00 04. Tue 07/07/2026 06:00 | Re-conditioning | TOTAL TRACK CLOSURE - DEERAL - ALOOMBA SUSPEND FOR MTP | Townsville Track Possessions
PB202511-00335 | Civil: 01. Mon 06/07/2026 06:00 02. Tue 07/07/2026 06:00 03. Wed 08/07/2026 06:00 04. Thu 09/07/2026 06:00 05. Fri 10/07/2026 06:00 | Civil: 01. Mon 06/07/2026 18:00 02. Tue 07/07/2026 18:00 03. Wed 08/07/2026 18:00 04. Thu 09/07/2026 18:00 05. Fri 10/07/2026 18:00 | Re-conditioning | PROSERPINE - BUBIALO **SUSPEND FOR MTP SERVICES ONLY*** | Townsville Track Possessions
PB202604-01582 | Civil: 01. Mon 13/07/2026 07:45 Isolation: 01. Mon 13/07/2026 07:00 | Civil: 01. Mon 13/07/2026 11:05 Isolation: 01. Mon 13/07/2026 11:05 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Theebine - Gundiah | Brisbane Track Possessions
PB202604-01591 | Civil: 01. Mon 20/07/2026 07:30 Isolation: 01. Mon 20/07/2026 07:00 | Civil: 01. Mon 20/07/2026 11:05 Isolation: 01. Mon 20/07/2026 11:05 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Paterson - Netherby | Brisbane Track Possessions
PB202603-01271 | Civil: 01. Tue 21/07/2026 06:00 | Civil: 01. Tue 21/07/2026 15:00 | General Mtce | Total Track Closure Innisfail - Waugh | Townsville Track Possessions
PB202503-01627 | Isolation: 01. Fri 31/07/2026 15:00 | Isolation: 01. Tue 04/08/2026 07:00 | NCL Shutdown | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202503-01628 | Isolation: 01. Fri 31/07/2026 15:45 | Isolation: 01. Tue 04/08/2026 07:00 | OHLE-generic NCL Shutdown | NNC ISOLATION MUNGAR - BUNDABERG | Brisbane Track Possessions
PB202503-01629 | Isolation: 01. Fri 31/07/2026 16:45 | Isolation: 01. Tue 04/08/2026 07:00 | ISOL REQ | ISOLATION NETLEY - BUNDABERG NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202503-01631 | Isolation: 01. Fri 31/07/2026 17:30 | Isolation: 01. Tue 04/08/2026 07:00 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202503-01632 | Isolation: 01. Fri 31/07/2026 17:30 | Isolation: 01. Tue 04/08/2026 07:00 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202509-00920 | Civil: 01. Sat 01/08/2026 06:30 | Civil: 01. Mon 03/08/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE (60 HR) SHUTDOWN & ISOLATION AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable Mt Miller Yard unavailable Moura Short Line unavailable | Townsville Track Possessions
PB202410-00613 | Civil: 01. Sat 01/08/2026 07:00 | Civil: 01. Tue 04/08/2026 04:00 | NNC Shutdown | TOTAL TRACK CLOSURE - MUNGAR & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01867 | Civil: 01. Sat 01/08/2026 09:00 | Civil: 01. Tue 04/08/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 72hrs ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202605-01179 | Civil: 01. Sat 01/08/2026 09:00 | Civil: 01. Tue 04/08/2026 17:00 | NCL Shutdown GIJ's | TOTAL TRACK CLOSURE CARMILLA - ORKABIE SECTION | Townsville Track Possessions
PB202605-00347 | Civil: 01. Sat 01/08/2026 13:00 | Civil: 01. Tue 04/08/2026 14:00 | Level Crossing | TOTAL TRACK CLOSURE - MOOKARA TO BOWEN JUNCTION NCL SHUTDOWN | Townsville Track Possessions
PB202605-00798 | Civil: 01. Sat 01/08/2026 13:30 | Civil: 01. Tue 04/08/2026 14:30 | NCL Shutdown Level Crossing | TOTAL TRACK CLOSURE MERINDA - DURROBURRA SECTION | Townsville Track Possessions
PB202311-01369 | Civil: 01. Sat 01/08/2026 14:00 | Civil: 01. Tue 04/08/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Tue Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Tue Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Tue Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202601-00250 | Civil: 01. Sat 01/08/2026 14:00 | Civil: 01. Tue 04/08/2026 14:00 | Bridge Const | TOTAL TRACK CLOSURE - Parkhurst - Glenmore JCT | Townsville Track Possessions
PB202603-01124 | Civil: 01. Sat 01/08/2026 14:30 | Civil: 01. Tue 04/08/2026 14:00 | Project | TOTAL TRACK CLOSURE - Rockhampton Yard and Mainline to Glenmore | Townsville Track Possessions
PB202503-00748 | Civil: 01. Sat 01/08/2026 20:00 | Civil: 01. Tue 04/08/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Tue Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Tue Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Tue Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202604-00063 | Civil: 01. Sat 01/08/2026 20:00 | Civil: 01. Tue 04/08/2026 18:00 | NCL Shutdown Cable route inst | TOTAL TRACK CLOSURE MACKAY 1 Road / Third Road not available for stowing | Townsville Track Possessions
PB202503-00749 | Civil: 01. Sun 02/08/2026 02:00 | Civil: 01. Wed 05/08/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202505-02003 | Civil: 01. Sun 02/08/2026 05:00 | Civil: 01. Wed 05/08/2026 05:00 | Re-conditioning | TOTAL CLOSURE - BOOGAN - SILKWOOD **SUSPEND FOR MTP TILT SERVICE ONLY** | Townsville Track Possessions
PB202603-01233 | Civil: 01. Sun 02/08/2026 05:00 | Civil: 01. Tue 04/08/2026 18:00 | Turnout Replace | TSV SUB TOTAL TRACK CLOSURE - THROUGH ROAD PARTINGTON YARD -Partington PI/Through Rd, to P8 closed from South End -No access into the South End of Partington Yard via Dn Rd/111B points -Dn Rd closed from Signal PN118 to PN 125 -Dead End Siding closed -Toll North Freight open -Sun Metals open -Copper Refinery open -Julago Cattle open -Access into Partington Yard from the North End only -P1 to P8 open from the North End only -Reduced stowage/storage capacity for P1 to P4 during closure times | Townsville Track Possessions
PB202603-00857 | Civil: 01. Sun 02/08/2026 06:40 | Civil: 01. Sun 02/08/2026 19:00 | Re-Stressing | TOTAL TRACK CLOSURE - Marlborough - Kooltandra | Townsville Track Possessions
PB202509-02106 | Civil: 01. Sun 02/08/2026 07:00 | Civil: 01. Wed 05/08/2026 07:00 | Project | TOTAL TRACK CLOSURE - WAUGH TO BABINDA NCL SHUTDOWN | Townsville Track Possessions
PB202503-00750 | Civil: 01. Sun 02/08/2026 09:00 | Civil: 01. Wed 05/08/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00858 | Civil: 01. Mon 03/08/2026 06:40 | Civil: 01. Mon 03/08/2026 19:00 | Re-Stressing | TOTAL TRACK CLOSURE - Ogmore - Wumalgi | Townsville Track Possessions
PB202501-02088 | Civil: 01. Tue 04/08/2026 18:00 | Civil: 01. Thu 06/08/2026 07:00 | Re-conditioning | Total Track Closure - Portsmith - Cairns (Suspend MTP Services Only) | Townsville Track Possessions
PB202605-00499 | Civil: 01. Fri 07/08/2026 10:00 | Civil: 01. Fri 07/08/2026 14:30 | GIJ's | TOTAL TRACK CLOSURE STUART - ANTILL PLAINS | Townsville Track Possessions
PB202604-01592 | Civil: 01. Mon 10/08/2026 07:30 Isolation: 01. Mon 10/08/2026 07:00 | Civil: 01. Mon 10/08/2026 11:05 Isolation: 01. Mon 10/08/2026 11:05 | OHLE-generic | TOTAL TRACK CLOSURE - ISOLATION - Gundiah - Tiaro | Brisbane Track Possessions
PB202603-01272 | Civil: 01. Tue 11/08/2026 06:00 | Civil: 01. Tue 11/08/2026 15:00 | General Mtce | Total Track Closure Waugh - Babinda | Townsville Track Possessions
PB202604-01352 | Civil: 01. Tue 01/09/2026 06:30 | Civil: 01. Thu 03/09/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AURIZON GOONYELLA SYSTEM INTEGRATED CLOSURE - 60 HOURS Aurizon Yukan Yard unavailable (QR Impact) NCL remains available for Freight and Passenger Traffic. | Townsville Track Possessions
PB202509-00922 | Civil: 01. Mon 28/09/2026 06:30 02. Tue 29/09/2026 06:30 03. Wed 30/09/2026 06:30 | Civil: 01. Mon 28/09/2026 18:30 02. Tue 29/09/2026 18:30 03. Wed 30/09/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION - AZJ NEWLANDS CLOSURE - FULL IMPACT TO NCL AT KAILI DURROBURRA Coal Leg between Kaili - Durroburra will be available overnight (between 1830 and 0630) for Freight and Passenger traffic. AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK | Townsville Track Possessions
PB202604-01353 | Civil: 01. Sun 11/10/2026 06:30 | Civil: 01. Thu 15/10/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AURIZON GOONYELLA SYSTEM INTEGRATED CLOSURE - 108HOURS Aurizon Yukan Yard unavailable (QR Impact) NCL remains available for Freight and Passenger Traffic. | Townsville Track Possessions
PB202507-02904 | 03. Fri 23/10/2026 03:30 04. Sat 24/10/2026 03:30 Civil: 01. Wed 21/10/2026 03:30 02. Thu 22/10/2026 03:30 | 03. Fri 23/10/2026 16:30 04. Sat 24/10/2026 16:30 Civil: 01. Wed 21/10/2026 16:30 02. Thu 22/10/2026 14:30 | Re-conditioning | TOTAL CLOSURE - BOOGAN - SILKWOOD **SUSPEND FOR MTP TILT SERVICE ONLY** | Townsville Track Possessions
PB202605-00730 | Civil: 01. Sat 24/10/2026 07:30 Isolation: 01. Fri 23/10/2026 15:30 | Civil: 01. Sun 25/10/2026 17:30 Isolation: 01. Mon 26/10/2026 10:00 | Re-Railing | TOTAL TRACK CLOSURE - ISOLATION - Tamaree Yard - Harvey's Siding | Brisbane Track Possessions
PB202503-01636 | Isolation: 01. Fri 23/10/2026 16:00 | Isolation: 01. Mon 26/10/2026 23:59 | NCL Shutdown OHLE-generic | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202503-01635 | Isolation: 01. Fri 23/10/2026 16:45 | Isolation: 01. Mon 26/10/2026 23:59 | ISOL REQ | ISOLATION NETLEY - BUNDABERG NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202503-01634 | Isolation: 01. Fri 23/10/2026 17:30 | Isolation: 01. Mon 26/10/2026 23:59 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202509-00923 | Civil: 01. Sat 24/10/2026 06:30 | Civil: 01. Tue 27/10/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW & MA IC & ISOLATION - NCL & CW LINE TOTAL IMPACT (84HR) Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202311-01884 | Civil: 01. Sat 24/10/2026 09:00 | Civil: 01. Tue 27/10/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HRS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202410-00609 | Civil: 01. Sat 24/10/2026 09:00 | Civil: 01. Mon 26/10/2026 23:59 | NNC Shutdown | TOTAL TRACK CLOSURE - PATERSON & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01371 | Civil: 01. Sat 24/10/2026 14:00 | Civil: 01. Tue 27/10/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202511-00379 | Civil: 01. Sat 24/10/2026 14:30 Isolation: 01. Sat 24/10/2026 14:30 | Civil: 01. Tue 27/10/2026 13:00 Isolation: 01. Tue 27/10/2026 13:00 | ISOL REQ General Mtce | TOTAL TRACK CLOSURE - Dead end road Rockhampton yard WORK BETWEEN TRAINS - Down Main Line ISOLATION - All roads isolated Rockhampton Yard | Townsville Track Possessions
PB202503-00751 | Civil: 01. Sat 24/10/2026 20:00 | Civil: 01. Tue 27/10/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202503-00752 | Civil: 01. Sun 25/10/2026 02:00 | Civil: 01. Wed 28/10/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202511-00744 | Civil: 01. Sun 25/10/2026 04:00 | Civil: 01. Wed 28/10/2026 04:00 | Re-conditioning | TOTAL TRACK CLOSURE - INGHAM - HINCHINBROOK NCL SHUTDOWN - REGIONAL | Townsville Track Possessions
PB202511-00740 | Civil: 01. Sun 25/10/2026 05:00 | Civil: 01. Wed 28/10/2026 05:00 | Re-conditioning | TOTAL CLOSURE - BOOGAN - SILKWOOD | Townsville Track Possessions
PB202508-00997 | Civil: 01. Sun 25/10/2026 05:30 | Civil: 01. Tue 27/10/2026 07:00 | Bridge Mtce | TOTAL TRACK CLOSURE - INNISFAIL - WAUGH | Townsville Track Possessions
PB202509-02107 | Civil: 01. Sun 25/10/2026 07:00 | Civil: 01. Wed 28/10/2026 07:00 | Project | TOTAL TRACK CLOSURE - WAUGH TO BABINDA | Townsville Track Possessions
PB202503-00753 | Civil: 01. Sun 25/10/2026 09:00 | Civil: 01. Wed 28/10/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202601-00729 | 04. Fri 06/11/2026 09:30 05. Sat 07/11/2026 09:30 06. Sun 08/11/2026 09:30 07. Mon 09/11/2026 09:30 08. Tue 10/11/2026 09:30 09. Wed 11/11/2026 09:30 Civil: 01. Tue 03/11/2026 09:30 02. Wed 04/11/2026 09:30 03. Thu 05/11/2026 09:30 | 04. Fri 06/11/2026 22:00 05. Sat 07/11/2026 22:00 06. Sun 08/11/2026 22:00 07. Mon 09/11/2026 22:00 08. Tue 10/11/2026 22:00 09. Wed 11/11/2026 22:00 Civil: 01. Tue 03/11/2026 22:00 02. Wed 04/11/2026 22:00 03. Thu 05/11/2026 22:00 | Re-Sleepering | TOTAL TRACK CLOSURE (PORTSMITH - CAIRNS) **SUSPEND FOR MTP SERVICES 1600 - 1800** **No traffic will be using the angle during the closure time** | Townsville Track Possessions
PB202208-01808 | Civil: 01. Fri 25/12/2026 17:00 | Civil: 01. Sat 26/12/2026 18:00 | Re-Railing | TOTAL TRACK CLOSURE BLOOMSBURY - THOOPARA | Townsville Track Possessions
PB202509-00830 | Isolation: 01. Fri 29/01/2027 15:30 | Isolation: 01. Mon 01/02/2027 10:00 | OHLE-generic NCL Shutdown | NNC ISOLATION CURRA TO WOKKA NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00828 | Isolation: 01. Fri 29/01/2027 16:30 | Isolation: 01. Mon 01/02/2027 09:00 | ISOL REQ NNC Shutdown | NNC ISOLATION ELLIOTT TO FLINDERS NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00827 | Isolation: 01. Fri 29/01/2027 17:30 | Isolation: 01. Mon 01/02/2027 08:00 | ISOL REQ | NNC CLOSURE ISOLATION - Korenan - Parana | Brisbane Track Possessions
PB202509-00926 | Civil: 01. Sat 30/01/2027 06:30 | Civil: 01. Sun 31/01/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION Central West Line - Rocklands to Tolmies and Crew. Callemondah Yard included. AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202509-00831 | Civil: 01. Sat 30/01/2027 07:00 | Civil: 01. Mon 01/02/2027 05:00 | NNC Shutdown | LPA - TOTAL TRACK CLOSURE - CURRA & MARYBOROUGH WEST TO FLINDERS | Brisbane Track Possessions
PB202103-01979 | Civil: 01. Sat 30/01/2027 14:00 | Civil: 01. Mon 01/02/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01888 | Civil: 01. Sat 30/01/2027 14:00 | Civil: 01. Mon 01/02/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN TRAIN ALTERATION ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202508-00545 | Civil: 01. Sat 30/01/2027 20:00 | Civil: 01. Mon 01/02/2027 18:00 | Level Crossing Turnout Replace | Total Track Closure - Proserpine Yard NCL - Shutdown | Townsville Track Possessions
PB202602-01465 | Civil: 01. Sat 30/01/2027 20:00 | Civil: 01. Mon 01/02/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202506-00463 | Civil: 01. Sun 31/01/2027 00:01 | Civil: 01. Mon 01/02/2027 22:00 | Re-conditioning | Total Track Closure Nome - Partington, UP Road Only No access to Julago | Townsville Track Possessions
PB202507-02223 | Civil: 01. Sun 31/01/2027 00:01 | Civil: 01. Mon 01/02/2027 22:00 | Re-conditioning | Total Track Closure Nome - Partington, UP Road Only No access to Julago | Townsville Track Possessions
PB202602-01467 | Civil: 01. Sun 31/01/2027 02:00 | Civil: 01. Tue 02/02/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202602-01475 | Civil: 01. Sun 31/01/2027 09:00 | Civil: 01. Tue 02/02/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202509-00931 | Civil: 01. Wed 03/03/2027 06:00 | Civil: 01. Thu 04/03/2027 18:00 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION North Coast Line available Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform available Gladstone Yard shunting available AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202511-00336 | Civil: 01. Mon 15/03/2027 06:00 02. Tue 16/03/2027 06:00 03. Wed 17/03/2027 06:00 04. Thu 18/03/2027 06:00 05. Fri 19/03/2027 06:00 | Civil: 01. Mon 15/03/2027 18:00 02. Tue 16/03/2027 18:00 03. Wed 17/03/2027 18:00 04. Thu 18/03/2027 18:00 05. Fri 19/03/2027 18:00 | Re-conditioning | TOTAL TRACK CLOSURE - PROSERPINE - BUBIALO **SUSPEND FOR MTP SERVICES ONLY*** | Townsville Track Possessions
PB202509-01702 | Civil: 01. Tue 16/03/2027 00:01 | Civil: 01. Fri 19/03/2027 00:01 | Culvert Renewal | TOTAL TRACK CLOSURE - NOME - PARTINGTON (UP/DOWN ROAD) NCL SHUTDOWN | Townsville Track Possessions
PB202509-00834 | Isolation: 01. Fri 02/04/2027 16:00 | Isolation: 01. Tue 06/04/2027 09:30 | NCL Shutdown OHLE-generic | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00835 | Isolation: 01. Fri 02/04/2027 16:30 | Isolation: 01. Tue 06/04/2027 09:00 | ISOL REQ | ISOLATION MUNGAR - FLINDERS NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00837 | Civil: 01. Sat 03/04/2027 06:20 | Civil: 01. Tue 06/04/2027 09:15 | NNC Shutdown | TOTAL TRACK CLOSURE - MUNGAR & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202509-00937 | Civil: 01. Sat 03/04/2027 06:30 | Civil: 01. Mon 05/04/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ GOONYELLA 60HR SHUTDOWN TOTAL IMPACT AT YUKAN (NCL & AZJ) AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK | Townsville Track Possessions
PB202508-01064 | Civil: 01. Sat 03/04/2027 09:00 | Civil: 01. Tue 06/04/2027 09:00 | NNC Shutdown | GENERAL INFORMATION- NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO AURIZON GOONYELLA SYSTEM CLOSURE Affected Trains -Freight, Travel, Livestock | Brisbane Track Possessions
PB202103-01980 | Civil: 01. Sat 03/04/2027 14:00 | Civil: 01. Tue 06/04/2027 14:00 | NCL Shutdown | GENERAL INFORMATION- NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO AURIZON GOONYELLA SYSTEM CLOSURE Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202510-01982 | Civil: 01. Sat 03/04/2027 20:00 | Civil: 01. Tue 06/04/2027 20:00 | Re-conditioning | TOTAL TRACK CLOSURE - PROSERPINE YARD NCL SHUTDOWN | Townsville Track Possessions
PB202601-01984 | Civil: 01. Sat 03/04/2027 23:00 | Civil: 01. Tue 06/04/2027 22:00 | Formation | TOTAL TRACK CLOSURE (NOME - CROMARTY) | Townsville Track Possessions
PB202509-00941 | Civil: 01. Mon 12/04/2027 06:30 | Civil: 01. Thu 15/04/2027 18:30 | Aurizon Shutdown | DRAFT GENERAL INFORMATION AZN BW CWL 84 HR SHUTDOWN & ISOLATION 8 HR NCL IMPACT - 12/04/2027 NCL Path available Rocklands Angle unavailable. Gracemere Tilt Maintenance Facility unavailable. Gladstone Platform available. Gladstone Yard shunting available. AFFECTED TRAINS: FREIGHT, PASSENGER, TRAVEL, LIVESTOCK | Townsville Track Possessions
PB202509-00840 | Isolation: 01. Fri 16/04/2027 16:00 | Isolation: 01. Tue 20/04/2027 09:30 | NCL Shutdown OHLE-generic | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00841 | Isolation: 01. Fri 16/04/2027 16:30 | Isolation: 01. Tue 20/04/2027 09:00 | ISOL REQ | ISOLATION MUNGAR - FLINDERS NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00838 | Civil: 01. Sat 17/04/2027 06:20 | Civil: 01. Tue 20/04/2027 06:20 | NNC Shutdown | TOTAL TRACK CLOSURE - MUNGAR & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01893 | Civil: 01. Sat 17/04/2027 09:00 | Civil: 01. Tue 20/04/2027 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HRS TRAIN ALTERATION ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains -Freight, Travel, Livestock | Brisbane Track Possessions
PB202508-01075 | Civil: 01. Sat 17/04/2027 14:00 | Civil: 01. Tue 20/04/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Tue Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Tue Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Tue Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Tue | Townsville Track Possessions
PB202603-00813 | Civil: 01. Sat 17/04/2027 20:00 | Civil: 01. Tue 20/04/2027 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Tue Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Tue Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Tue Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Wed | Townsville Track Possessions
PB202603-00814 | Civil: 01. Sun 18/04/2027 02:00 | Civil: 01. Wed 21/04/2027 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00815 | Civil: 01. Sun 18/04/2027 09:00 | Civil: 01. Wed 21/04/2027 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202604-01204 | Civil: 01. Sat 24/04/2027 05:30 | Civil: 01. Mon 26/04/2027 16:30 | Bridge Mtce | TOTAL TRACK CLOSURE - INNISFAIL - WAUGH | Townsville Track Possessions
PB202509-00842 | Isolation: 01. Fri 21/05/2027 15:00 | Isolation: 01. Thu 27/05/2027 10:00 | NCL Shutdown OHLE-generic | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00843 | Isolation: 01. Fri 21/05/2027 16:00 | Isolation: 01. Thu 27/05/2027 09:30 | NCL Shutdown OHLE-generic | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00844 | Isolation: 01. Fri 21/05/2027 17:00 | Isolation: 01. Thu 27/05/2027 09:00 | ISOL REQ | ISOLATION NETLEY - BUNDABERG NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00845 | Isolation: 01. Fri 21/05/2027 17:30 | Isolation: 01. Thu 27/05/2027 08:00 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202509-00946 | Civil: 01. Sat 22/05/2027 06:30 | Civil: 01. Wed 26/05/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BLACKWATER & MOURA IC AND ISOLATION - TOTAL IMPACT TO CW & NCL LINE 108 HR Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202509-00848 | Civil: 01. Sat 22/05/2027 07:00 | Civil: 01. Thu 27/05/2027 08:00 | NNC Shutdown | TOTAL TRACK CLOSURE - PATERSON & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01380 | Civil: 01. Sat 22/05/2027 14:00 | Civil: 01. Thu 27/05/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Thu Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Thu Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Thu Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Thu All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01904 | Civil: 01. Sat 22/05/2027 14:00 | Civil: 01. Wed 26/05/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202603-00821 | Civil: 01. Sat 22/05/2027 20:00 | Civil: 01. Thu 27/05/2027 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 DAYS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Thu Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Thu Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Thu Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202601-00579 | Civil: 01. Sat 22/05/2027 23:30 | Civil: 01. Wed 26/05/2027 23:00 | Formation | TOTAL TRACK CLOSURE (NOME - CROMARTY) ***INCLUDING SUGAR TRAINS*** AS REQUESTED BY DAVE CABASSI AND LUKE O'NEILL | Townsville Track Possessions
PB202508-01444 | Civil: 01. Sun 23/05/2027 02:00 | Civil: 01. Thu 27/05/2027 02:00 | Level Crossing | TOTAL TRACK CLOSURE - OONOONBA - TSV FORK NCL / MIL SHUTDOWN | Townsville Track Possessions
PB202603-00822 | Civil: 01. Sun 23/05/2027 02:00 | Civil: 01. Fri 28/05/2027 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Fri Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Fri Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Fri Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00823 | Civil: 01. Sun 23/05/2027 09:00 | Civil: 01. Fri 28/05/2027 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days ALIGNED TO SEQ NCL SCAS Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202408-00678 | Civil: 01. Sun 23/05/2027 22:00 | Civil: 01. Wed 26/05/2027 18:00 | Level Crossing | TOTAL TRACK CLOSURE - PROSERPINE YARD / PROSERPINE - BUBIALO | Townsville Track Possessions
PB202602-00346 | Civil: 01. Tue 01/06/2027 06:30 | Civil: 01. Fri 04/06/2027 18:00 | Turnout Replace | TOTAL TRACK CLOSURE - TOWNSVILLE JETTY BLUE ROAD | Townsville Track Possessions
PB202509-00849 | Isolation: 01. Fri 16/07/2027 15:00 | Isolation: 01. Mon 19/07/2027 07:00 | NCL Shutdown | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00850 | Isolation: 01. Fri 16/07/2027 15:45 | Isolation: 01. Mon 19/07/2027 07:00 | OHLE-generic NCL Shutdown | NNC ISOLATION MUNGAR - BUNDABERG | Brisbane Track Possessions
PB202509-00851 | Isolation: 01. Fri 16/07/2027 16:45 | Isolation: 01. Mon 19/07/2027 07:00 | ISOL REQ | ISOLATION NETLEY - BUNDABERG NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00852 | Isolation: 01. Fri 16/07/2027 17:30 | Isolation: 01. Mon 19/07/2027 07:00 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202509-00854 | Civil: 01. Sat 17/07/2027 07:00 | Civil: 01. Mon 19/07/2027 04:00 | NNC Shutdown | TOTAL TRACK CLOSURE - MUNGAR & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01912 | Civil: 01. Sat 17/07/2027 09:00 | Civil: 01. Mon 19/07/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 46HRS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202311-01382 | Civil: 01. Sat 17/07/2027 14:00 | Civil: 01. Mon 19/07/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00830 | Civil: 01. Sat 17/07/2027 20:00 | Civil: 01. Mon 19/07/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon | Townsville Track Possessions
PB202603-00832 | Civil: 01. Sun 18/07/2027 02:00 | Civil: 01. Tue 20/07/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00833 | Civil: 01. Sun 18/07/2027 09:00 | Civil: 01. Tue 20/07/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202509-00855 | Isolation: 01. Fri 15/10/2027 16:00 | Isolation: 01. Mon 18/10/2027 23:59 | OHLE-generic NCL Shutdown | NNC ISOLATION MUNGAR - TAMAREE | Brisbane Track Possessions
PB202509-00856 | Isolation: 01. Fri 15/10/2027 16:45 | Isolation: 01. Mon 18/10/2027 23:59 | ISOL REQ | ISOLATION NETLEY - BUNDABERG NIL ELECTRICS TRAIN ALERATIONS ALIGNED TO SEQ / REG NCL SHUTDOWN | Brisbane Track Possessions
PB202509-00857 | Isolation: 01. Fri 15/10/2027 17:30 | Isolation: 01. Mon 18/10/2027 23:59 | ISOL REQ | ISOLATION NETLEY - PARANA NIL ELECTRICS | Brisbane Track Possessions
PB202509-00858 | Civil: 01. Sat 16/10/2027 09:00 | Civil: 01. Mon 18/10/2027 23:59 | NNC Shutdown | TOTAL TRACK CLOSURE - PATERSON & MARYBOROUGH WEST TO FLINDERS NNC CLOSURE | Brisbane Track Possessions
PB202311-01383 | Civil: 01. Sat 16/10/2027 14:00 | Civil: 01. Mon 18/10/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01915 | Civil: 01. Sat 16/10/2027 14:00 | Civil: 01. Mon 18/10/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202603-00839 | Civil: 01. Sat 16/10/2027 20:00 | Civil: 01. Mon 18/10/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1900 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00841 | Civil: 01. Sun 17/10/2027 02:00 | Civil: 01. Tue 19/10/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00843 | Civil: 01. Sun 17/10/2027 09:00 | Civil: 01. Tue 19/10/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202604-01205 | Civil: 01. Mon 25/10/2027 05:30 | Civil: 01. Wed 27/10/2027 16:30 | Bridge Mtce | TOTAL TRACK CLOSURE - INNISFAIL - WAUGH | Townsville Track Possessions
PB202604-00718 | Civil: 01. Sat 12/02/2028 09:00 | Civil: 01. Mon 14/02/2028 07:00 | NNC Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID SEQ NCL SCAS / REG SHUTDOWN BNE - WOREE TRAIN ALTERATION ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN | Brisbane Track Possessions
PB202103-01983 | Civil: 01. Sat 12/02/2028 14:00 | Civil: 01. Mon 14/02/2028 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID SEQ NCL SCAS / REG SHUTDOWN BNE - WOREE TRAIN ALTERATION ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN | Townsville Track Possessions
PB202103-01984 | Civil: 01. Sat 25/03/2028 14:00 | Civil: 01. Mon 27/03/2028 12:00 | NCL Shutdown | TOTAL CLOSURE - NO TRAINS GENERAL INFORMATION BID SEQ NCL SCAS / REG SHUTDOWN BNE - WOREE TRAIN ALTERATIONS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN | Townsville Track Possessions
PB202508-01635 | Civil: 01. Fri 14/04/2028 09:00 | Civil: 01. Wed 19/04/2028 09:00 | NNC Shutdown | **DRAFT - DATES TO BE CONFIRMED** TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock | Brisbane Track Possessions
PB202508-01634 | Civil: 01. Fri 14/04/2028 14:00 | Civil: 01. Wed 19/04/2028 14:00 | NCL Shutdown | **DRAFT - DATES TO BE CONFIRMED** TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions

## Central West
Regional Operations: NCL Possession Calendar 19/05/2026 - 19/05/2028
Townsville System: Central West - Emerald to Winton.
Pb Number | Start Date | End Date | Work Types | Traffic Comments | Possession Territory
PB202604-00824 | Civil: 01. Tue 19/05/2026 07:00 02. Wed 20/05/2026 07:00 | Civil: 01. Tue 19/05/2026 15:00 02. Wed 20/05/2026 15:00 | Yard Mtce | TOTAL TRACK CLOSURE NOGOA - EMERALD - YAMBOYNA SUSPEND FOR MTP SERVICES ONLY | Townsville Track Possessions
PB202311-01376 | Civil: 01. Sat 23/05/2026 14:00 | Civil: 01. Thu 28/05/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Thu Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Thu Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Thu Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Thu All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01866 | Civil: 01. Sat 23/05/2026 14:00 | Civil: 01. Thu 28/05/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 120 HOURS Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202503-00744 | Civil: 01. Sat 23/05/2026 20:00 | Civil: 01. Thu 28/05/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 DAYS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Thu Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Thu Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Thu Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202503-00745 | Civil: 01. Sun 24/05/2026 02:00 | Civil: 01. Fri 29/05/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Fri Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Fri Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Fri Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202410-01778 | Civil: 01. Sun 24/05/2026 06:30 | Civil: 01. Wed 27/05/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE SHUTDOWN (84HRS) & ISOLATION (TBC) AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK. NIL ELECTRICS | Townsville Track Possessions
PB202410-01779 | Civil: 01. Sun 24/05/2026 06:30 | Civil: 01. Thu 28/05/2026 06:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE SHUTDOWN (96HRS) & ISOLATION (TBC) AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK. NIL ELECTRICS | Townsville Track Possessions
PB202503-00747 | Civil: 01. Sun 24/05/2026 09:00 | Civil: 01. Fri 29/05/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days ALIGNED TO SEQ NCL SCAS Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202604-00112 | Civil: 01. Tue 26/05/2026 07:00 | Civil: 01. Mon 01/06/2026 16:00 | General Mtce | TA MAJOR - TOTAL TRACK CLOSURE - CRAMSIE ANGLE & CATTLE SIDING NIL IMPACT TO RAIL TRAFFIC | Townsville Track Possessions
PB202510-00926 | Civil: 01. Thu 28/05/2026 07:00 | Civil: 01. Thu 28/05/2026 17:00 | Turnout Mtce | TOTAL TRACK CLOSURE - DILLCAR - WINTON YARD CAN SUSPEND FOR MTP SERVICES ONLY | Townsville Track Possessions
PB202510-00943 | Civil: 01. Sun 31/05/2026 07:00 02. Mon 01/06/2026 07:00 03. Tue 02/06/2026 07:00 | Civil: 01. Sun 31/05/2026 16:00 02. Mon 01/06/2026 16:00 03. Tue 02/06/2026 16:00 | Turnout Mtce | TOTAL TRACK CLOSURE - EMERALD YARD - NOGOA CAN SUSPEND FOR MTP TRAINS ONLY IF REQUIRED | Townsville Track Possessions
PB202602-01496 | Civil: 01. Tue 09/06/2026 06:20 02. Wed 10/06/2026 06:20 | Civil: 01. Tue 09/06/2026 16:00 02. Wed 10/06/2026 16:00 | Level Crossing | TOTAL TRACK CLOSURE - EMERALD TO YAMBOYNA Unable to Suspend | Townsville Track Possessions
PB202510-00056 | Civil: 01. Fri 19/06/2026 06:00 | Civil: 01. Sun 21/06/2026 12:00 | Signals-generic | TOTAL TRACK CLOSURE - BARCALDINE to LOCHNAGAR SUSPEND FOR NOMINATED SERVICES ONLY | Townsville Track Possessions
PB202509-01412 | Civil: 01. Tue 23/06/2026 07:00 | Civil: 01. Sat 27/06/2026 18:00 | Re-Surfacing Relay-Operations | Total Track Closure from Down LOS Duchess to UP LOS Woonigan. | Townsville Track Possessions
PB202510-00929 | Civil: 01. Thu 30/07/2026 07:00 | Civil: 01. Thu 30/07/2026 17:00 | Turnout Mtce | total closure Dillcar - Winton Yard | Townsville Track Possessions
PB202509-00920 | Civil: 01. Sat 01/08/2026 06:30 | Civil: 01. Mon 03/08/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE (60 HR) SHUTDOWN & ISOLATION AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable Mt Miller Yard unavailable Moura Short Line unavailable | Townsville Track Possessions
PB202509-00921 | Civil: 01. Sat 01/08/2026 06:30 | Civil: 01. Mon 03/08/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW NCL & CW LINE (60 HR) SHUTDOWN & ISOLATION AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202311-01369 | Civil: 01. Sat 01/08/2026 14:00 | Civil: 01. Tue 04/08/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Tue Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Tue Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Tue Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01882 | Civil: 01. Sat 01/08/2026 14:00 | Civil: 01. Tue 04/08/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202503-00748 | Civil: 01. Sat 01/08/2026 20:00 | Civil: 01. Tue 04/08/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Tue Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Tue Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Tue Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202503-00749 | Civil: 01. Sun 02/08/2026 02:00 | Civil: 01. Wed 05/08/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202510-00944 | Civil: 01. Sun 02/08/2026 07:00 02. Mon 03/08/2026 07:00 | Civil: 01. Sun 02/08/2026 16:00 02. Mon 03/08/2026 16:00 | Turnout Mtce | TOTAL TRACK CLOSURE - EMERALD YARD - NOGOA CAN SUSPEND FOR MTP TRAINS ONLY IF REQUIRED | Townsville Track Possessions
PB202503-00750 | Civil: 01. Sun 02/08/2026 09:00 | Civil: 01. Wed 05/08/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202508-00350 | Civil: 01. Tue 25/08/2026 07:00 | Civil: 01. Fri 28/08/2026 18:00 | Re-Sleepering Undercutting | Total Track Closure Homestead Yard. | Townsville Track Possessions
PB202510-00930 | Civil: 01. Thu 24/09/2026 07:00 | Civil: 01. Thu 24/09/2026 17:00 | Turnout Mtce | TOTAL TRACK CLOSURE - DILLCAR - WINTON YARD CAN SUSPEND FOR MTP SERVICES | Townsville Track Possessions
PB202510-00980 | Civil: 01. Sun 27/09/2026 07:00 02. Mon 28/09/2026 07:00 | Civil: 01. Sun 27/09/2026 16:00 02. Mon 28/09/2026 16:00 | Turnout Mtce | TOTAL TRACK CLOSURE - EMERALD YARD - NOGOA CAN SUSPEND FOR MTP TRAINS ONLY IF REQUIRED | Townsville Track Possessions
PB202510-00063 | Civil: 01. Thu 01/10/2026 06:00 | Civil: 01. Sun 04/10/2026 18:00 | Signals-generic | TOTAL TRACK CLOSURE - BARCALDINE to SALTERN CAN SUSPEND FOR MTP SERVICES | Townsville Track Possessions
PB202508-01129 | Civil: 01. Wed 07/10/2026 07:00 | Civil: 01. Wed 07/10/2026 19:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202510-01930 | Civil: 01. Thu 08/10/2026 07:00 | Civil: 01. Thu 08/10/2026 15:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202508-01133 | Civil: 01. Sat 10/10/2026 07:00 | Civil: 01. Sat 10/10/2026 19:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202510-01931 | Civil: 01. Sun 11/10/2026 07:00 | Civil: 01. Sun 11/10/2026 15:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202509-00923 | Civil: 01. Sat 24/10/2026 06:30 | Civil: 01. Tue 27/10/2026 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW & MA IC & ISOLATION - NCL & CW LINE TOTAL IMPACT (84HR) Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202311-01371 | Civil: 01. Sat 24/10/2026 14:00 | Civil: 01. Tue 27/10/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01885 | Civil: 01. Sat 24/10/2026 14:00 | Civil: 01. Tue 27/10/2026 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202503-00751 | Civil: 01. Sat 24/10/2026 20:00 | Civil: 01. Tue 27/10/2026 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202503-00752 | Civil: 01. Sun 25/10/2026 02:00 | Civil: 01. Wed 28/10/2026 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202503-00753 | Civil: 01. Sun 25/10/2026 09:00 | Civil: 01. Wed 28/10/2026 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202508-01128 | Civil: 01. Wed 04/11/2026 07:00 | Civil: 01. Wed 04/11/2026 19:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202510-01932 | Civil: 01. Thu 05/11/2026 07:00 | Civil: 01. Thu 05/11/2026 15:00 | Turnout Mtce | Total Track Closure Woonigan Yard. | Townsville Track Possessions
PB202510-00932 | Civil: 01. Thu 26/11/2026 07:00 | Civil: 01. Thu 26/11/2026 17:00 | Turnout Mtce | TOTAL TRACK CLOSURE - DILLCAR - WINTON YARD CAN SUSPSEND FOR MTP TRAFFICE | Townsville Track Possessions
PB202510-00981 | Civil: 01. Sun 29/11/2026 07:00 02. Mon 30/11/2026 07:00 | Civil: 01. Sun 29/11/2026 16:00 02. Mon 30/11/2026 16:00 | Turnout Mtce | TOTAL TRACK CLOSURE - EMERALD YARD - NOGOA CAN SUSPEND FOR MTP TRAINS ONLY IF REQUIRED | Townsville Track Possessions
PB202506-01471 | Civil: 01. Tue 01/12/2026 07:00 | Civil: 01. Tue 01/12/2026 18:00 | Re-Stressing | Total Track Closure Down LOS Reid River to UP LOS Woldston. | Townsville Track Possessions
PB202509-00925 | Civil: 01. Sat 30/01/2027 06:30 | Civil: 01. Sun 31/01/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION Central West Line - Rocklands to Tolmies and Crew. Callemondah Yard included. AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202509-00926 | Civil: 01. Sat 30/01/2027 06:30 | Civil: 01. Sun 31/01/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION Central West Line - Rocklands to Tolmies and Crew. Callemondah Yard included. AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202103-01979 | Civil: 01. Sat 30/01/2027 14:00 | Civil: 01. Mon 01/02/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01890 | Civil: 01. Sat 30/01/2027 14:00 | Civil: 01. Mon 01/02/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HRS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202602-01465 | Civil: 01. Sat 30/01/2027 20:00 | Civil: 01. Mon 01/02/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202602-01467 | Civil: 01. Sun 31/01/2027 02:00 | Civil: 01. Tue 02/02/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202602-01475 | Civil: 01. Sun 31/01/2027 09:00 | Civil: 01. Tue 02/02/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202509-00931 | Civil: 01. Wed 03/03/2027 06:00 | Civil: 01. Thu 04/03/2027 18:00 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION North Coast Line available Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform available Gladstone Yard shunting available AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202509-00932 | Civil: 01. Wed 03/03/2027 06:00 | Civil: 01. Thu 04/03/2027 18:00 | Aurizon Shutdown | GENERAL INFORMATION AZJ BW CW LINE 36HR SHUTDOWN & ISOLATION North Coast Line available Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform available Gladstone Yard shunting available AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202311-01899 | Civil: 01. Sat 03/04/2027 14:00 | Civil: 01. Tue 06/04/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HRS ALIGNED TO AURIZON GOONYELLA SYSTEM CLOSURE Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202509-00941 | Civil: 01. Mon 12/04/2027 06:30 | Civil: 01. Thu 15/04/2027 18:30 | Aurizon Shutdown | DRAFT GENERAL INFORMATION AZN BW CWL 84 HR SHUTDOWN & ISOLATION 8 HR NCL IMPACT - 12/04/2027 NCL Path available Rocklands Angle unavailable. Gracemere Tilt Maintenance Facility unavailable. Gladstone Platform available. Gladstone Yard shunting available. AFFECTED TRAINS: FREIGHT, PASSENGER, TRAVEL, LIVESTOCK | Townsville Track Possessions
PB202509-00944 | Civil: 01. Mon 12/04/2027 06:30 | Civil: 01. Thu 15/04/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZN BW CWL 84 HR SHUTDOWN & ISOLATION 8 HR NCL IMPACT - 12/04/2027 NCL Path available Rocklands Angle unavailable. Gracemere Tilt Maintenance Facility unavailable. Gladstone Platform available. Gladstone Yard shunting available. AFFECTED TRAINS: FREIGHT, PASSENGER, TRAVEL, LIVESTOCK | Townsville Track Possessions
PB202508-01075 | Civil: 01. Sat 17/04/2027 14:00 | Civil: 01. Tue 20/04/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 72 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Tue Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Tue Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Tue Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Tue | Townsville Track Possessions
PB202603-00813 | Civil: 01. Sat 17/04/2027 20:00 | Civil: 01. Tue 20/04/2027 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Tue Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Tue Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Tue Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Wed | Townsville Track Possessions
PB202603-00814 | Civil: 01. Sun 18/04/2027 02:00 | Civil: 01. Wed 21/04/2027 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Wed Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Wed Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Wed Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Wed Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00815 | Civil: 01. Sun 18/04/2027 09:00 | Civil: 01. Wed 21/04/2027 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 72 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Wed All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202509-00946 | Civil: 01. Sat 22/05/2027 06:30 | Civil: 01. Wed 26/05/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BLACKWATER & MOURA IC AND ISOLATION - TOTAL IMPACT TO CW & NCL LINE 108 HR Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202509-00948 | Civil: 01. Sat 22/05/2027 06:30 | Civil: 01. Wed 26/05/2027 18:30 | Aurizon Shutdown | GENERAL INFORMATION AZJ BLACKWATER & MOURA IC AND ISOLATION - TOTAL IMPACT TO CW & NCL LINE 108 HR Rocklands Angle unavailable Gracemere Tilt Maintenance Facility unavailable Gladstone Platform unavailable Gladstone Yard shunting unavailable AFFECTED TRAINS: FREIGHT, PASSENGER, LIVESTOCK, NIL ELECTRICS | Townsville Track Possessions
PB202311-01380 | Civil: 01. Sat 22/05/2027 14:00 | Civil: 01. Thu 27/05/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN (5 DAYS) Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1200 Thu Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1400 Thu Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1530 Thu Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1700 Thu All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01906 | Civil: 01. Sat 22/05/2027 14:00 | Civil: 01. Thu 27/05/2027 14:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 5 DAYS Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202603-00821 | Civil: 01. Sat 22/05/2027 20:00 | Civil: 01. Thu 27/05/2027 20:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 DAYS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 2000 Thu Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2200 Thu Gumlu to Nome Start Time - 2330 Sat Finish Time - 2330 Thu Nome to Partington Start Time - 0001 Sun Finish Time - 0001 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00822 | Civil: 01. Sun 23/05/2027 02:00 | Civil: 01. Fri 28/05/2027 02:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0200 Fri Ingham to Tully Start Time - 0400 Sun Finish Time - 0400 Fri Tully to Innisfail Start Time - 0500 Sun Finish Time - 0500 Fri Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0700 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00823 | Civil: 01. Sun 23/05/2027 09:00 | Civil: 01. Fri 28/05/2027 09:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 5 Days ALIGNED TO SEQ NCL SCAS Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0900 Fri All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01382 | Civil: 01. Sat 17/07/2027 14:00 | Civil: 01. Mon 19/07/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01913 | Civil: 01. Sat 17/07/2027 14:00 | Civil: 01. Mon 19/07/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HRS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202603-00830 | Civil: 01. Sat 17/07/2027 20:00 | Civil: 01. Mon 19/07/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1800 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon | Townsville Track Possessions
PB202603-00832 | Civil: 01. Sun 18/07/2027 02:00 | Civil: 01. Tue 20/07/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00833 | Civil: 01. Sun 18/07/2027 09:00 | Civil: 01. Tue 20/07/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01383 | Civil: 01. Sat 16/10/2027 14:00 | Civil: 01. Mon 18/10/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HOURS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times RTN - MKY Rocklands to Rockhampton Start Time - 1200 Sat Finish Time - 1000 Mon Rockhampton to Princhester Start Time - 1400 Sat Finish Time - 1200 Mon Princhester to Orkabie Start Time - 1530 Sat Finish Time - 1330 Mon Orkabie to Mackay Start Time - 1700 Sat Finish Time - 1500 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202311-01916 | Civil: 01. Sat 16/10/2027 14:00 | Civil: 01. Mon 18/10/2027 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID - REGIONAL NORTH COAST LINE SHUTDOWN - 46 HRS ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN Affected Trains - Freight, Travel, Livestock | Townsville Track Possessions
PB202603-00839 | Civil: 01. Sat 16/10/2027 20:00 | Civil: 01. Mon 18/10/2027 18:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times MKY- TSV Mackay to Proserpine Start Time - 2000 Sat Finish Time - 1900 Mon Proserpine to Gumlu Start Time - 2200 Sat Finish Time - 2000 Mon Gumlu to Nome Start Time - 2330 Sat Finish Time - 2130 Mon Nome to Partington Start Time - 0001 Sun Finish Time - 2200 Mon All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00841 | Civil: 01. Sun 17/10/2027 02:00 | Civil: 01. Tue 19/10/2027 00:01 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times TSV - CNS Townsville to Ingham Start Time - 0200 Sun Finish Time - 0001 Tue Ingham to Tully Start Time - 0400 Sun Finish Time - 0200 Tue Tully to Innisfail Start Time - 0500 Sun Finish Time - 0300 Tue Innisfail to Deeral Start Time - 0700 Sun Finish Time - 0500 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202603-00843 | Civil: 01. Sun 17/10/2027 09:00 | Civil: 01. Tue 19/10/2027 07:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION - REGIONAL NORTH COAST LINE SHUTDOWN 46 HOURS ALIGNED TO SEQ NCL SCAS Affected Trains - Freight, Travel, Livestock Indicative NCL Shutdown Possession Times Deeral to Portsmith Start Time - 0900 Sun Finish Time - 0700 Tue All scheduled times are provisional and may be subject to modification based on the completion of any alterations or cancellations of services, in order to accommodate capacity adjustments or other operational or business requirements. Brisbane Train Control & Planning reserves the right to determine the final schedules and will communicate any changes in accordance with established protocols. | Townsville Track Possessions
PB202103-01983 | Civil: 01. Sat 12/02/2028 14:00 | Civil: 01. Mon 14/02/2028 12:00 | NCL Shutdown | TOTAL CLOSURE - GENERAL INFORMATION BID SEQ NCL SCAS / REG SHUTDOWN BNE - WOREE TRAIN ALTERATION ALIGNED TO SEQ NCL SCAS / REG SHUTDOWN | Townsville Track Possessions

## Tablelands
Regional Operations: NCL Possession Calendar 19/05/2026 - 19/05/2028
Townsville System: Tablelands - Cairns to Normanton.
Pb Number | Start Date | End Date | Work Types | Traffic Comments | Possession Territory
PB202604-01273 | Civil: 01. Mon 27/04/2026 08:00 | Civil: 01. Mon 29/06/2026 07:59 | Other | TEMPORARY SUSPENSION OF THE SAFEWORKING SYSTEM EINASLEIGH – FORSAYTH | Townsville Track Possessions
PB202512-00830 | Civil: 01. Mon 18/05/2026 05:00 02. Tue 19/05/2026 05:00 03. Wed 20/05/2026 05:00 04. Thu 21/05/2026 05:00 05. Fri 22/05/2026 05:00 06. Sat 23/05/2026 05:00 | Civil: 01. Tue 19/05/2026 04:00 02. Wed 20/05/2026 04:00 03. Thu 21/05/2026 04:00 04. Fri 22/05/2026 04:00 05. Sat 23/05/2026 04:00 06. Sun 24/05/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00831 | Civil: 01. Mon 25/05/2026 05:00 02. Tue 26/05/2026 05:00 03. Wed 27/05/2026 05:00 04. Thu 28/05/2026 05:00 05. Fri 29/05/2026 05:00 06. Sat 30/05/2026 05:00 | Civil: 01. Tue 26/05/2026 04:00 02. Wed 27/05/2026 04:00 03. Thu 28/05/2026 04:00 04. Fri 29/05/2026 04:00 05. Sat 30/05/2026 04:00 06. Sun 31/05/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00832 | Civil: 01. Mon 01/06/2026 05:00 02. Tue 02/06/2026 05:00 03. Wed 03/06/2026 05:00 04. Thu 04/06/2026 05:00 05. Fri 05/06/2026 05:00 06. Sat 06/06/2026 05:00 | Civil: 01. Tue 02/06/2026 04:00 02. Wed 03/06/2026 04:00 03. Thu 04/06/2026 04:00 04. Fri 05/06/2026 04:00 05. Sat 06/06/2026 04:00 06. Sun 07/06/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00833 | Civil: 01. Mon 08/06/2026 05:00 02. Tue 09/06/2026 05:00 03. Wed 10/06/2026 05:00 04. Thu 11/06/2026 05:00 05. Fri 12/06/2026 05:00 06. Sat 13/06/2026 05:00 | Civil: 01. Tue 09/06/2026 04:00 02. Wed 10/06/2026 04:00 03. Thu 11/06/2026 04:00 04. Fri 12/06/2026 04:00 05. Sat 13/06/2026 04:00 06. Sun 14/06/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202505-00625 | Civil: 01. Sun 14/06/2026 17:30 | Civil: 01. Fri 19/06/2026 18:00 | General Mtce | TOTAL TRACK CLOSURE (REDLYNCH - KURANDA) TRAINS AFFECTED: TRAVEL | Townsville Track Possessions
PB202512-00835 | Civil: 01. Sat 20/06/2026 05:00 | Civil: 01. Sat 20/06/2026 18:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00836 | Civil: 01. Mon 22/06/2026 05:00 02. Tue 23/06/2026 05:00 03. Wed 24/06/2026 05:00 04. Thu 25/06/2026 05:00 05. Fri 26/06/2026 05:00 06. Sat 27/06/2026 05:00 | Civil: 01. Tue 23/06/2026 04:00 02. Wed 24/06/2026 04:00 03. Thu 25/06/2026 04:00 04. Fri 26/06/2026 04:00 05. Sat 27/06/2026 04:00 06. Sun 28/06/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00837 | Civil: 01. Mon 29/06/2026 05:00 02. Tue 30/06/2026 05:00 03. Wed 01/07/2026 05:00 04. Thu 02/07/2026 05:00 05. Fri 03/07/2026 05:00 06. Sat 04/07/2026 05:00 | Civil: 01. Tue 30/06/2026 04:00 02. Wed 01/07/2026 04:00 03. Thu 02/07/2026 04:00 04. Fri 03/07/2026 04:00 05. Sat 04/07/2026 04:00 06. Sun 05/07/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00838 | Civil: 01. Mon 06/07/2026 05:00 02. Tue 07/07/2026 05:00 03. Wed 08/07/2026 05:00 04. Thu 09/07/2026 05:00 05. Fri 10/07/2026 05:00 06. Sat 11/07/2026 05:00 | Civil: 01. Tue 07/07/2026 04:00 02. Wed 08/07/2026 04:00 03. Thu 09/07/2026 04:00 04. Fri 10/07/2026 04:00 05. Sat 11/07/2026 04:00 06. Sun 12/07/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00839 | Civil: 01. Mon 13/07/2026 05:00 02. Tue 14/07/2026 05:00 03. Wed 15/07/2026 05:00 04. Thu 16/07/2026 05:00 05. Fri 17/07/2026 05:00 06. Sat 18/07/2026 05:00 | Civil: 01. Tue 14/07/2026 04:00 02. Wed 15/07/2026 04:00 03. Thu 16/07/2026 04:00 04. Fri 17/07/2026 04:00 05. Sat 18/07/2026 04:00 06. Sun 19/07/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00840 | 06. Sat 25/07/2026 05:00 Civil: 01. Mon 20/07/2026 05:00 02. Tue 21/07/2026 05:00 03. Wed 22/07/2026 05:00 04. Thu 23/07/2026 05:00 05. Fri 24/07/2026 05:00 | 06. Sun 26/07/2026 04:00 Civil: 01. Tue 21/07/2026 04:00 02. Wed 22/07/2026 04:00 03. Thu 23/07/2026 04:00 04. Fri 24/07/2026 04:00 05. Sat 25/07/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00841 | Civil: 01. Mon 27/07/2026 05:00 02. Tue 28/07/2026 05:00 03. Wed 29/07/2026 05:00 04. Thu 30/07/2026 05:00 05. Fri 31/07/2026 05:00 06. Sat 01/08/2026 05:00 | Civil: 01. Tue 28/07/2026 04:00 02. Wed 29/07/2026 04:00 03. Thu 30/07/2026 04:00 04. Fri 31/07/2026 04:00 05. Sat 01/08/2026 04:00 06. Sun 02/08/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00842 | Civil: 01. Mon 03/08/2026 05:00 02. Tue 04/08/2026 05:00 03. Wed 05/08/2026 05:00 04. Thu 06/08/2026 05:00 05. Fri 07/08/2026 05:00 06. Sat 08/08/2026 05:00 | Civil: 01. Tue 04/08/2026 04:00 02. Wed 05/08/2026 04:00 03. Thu 06/08/2026 04:00 04. Fri 07/08/2026 04:00 05. Sat 08/08/2026 04:00 06. Sun 09/08/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00843 | Civil: 01. Mon 10/08/2026 05:00 02. Tue 11/08/2026 05:00 03. Wed 12/08/2026 05:00 04. Thu 13/08/2026 05:00 05. Fri 14/08/2026 05:00 06. Sat 15/08/2026 05:00 | Civil: 01. Tue 11/08/2026 04:00 02. Wed 12/08/2026 04:00 03. Thu 13/08/2026 04:00 04. Fri 14/08/2026 04:00 05. Sat 15/08/2026 04:00 06. Sun 16/08/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00844 | Civil: 01. Mon 17/08/2026 05:00 02. Tue 18/08/2026 05:00 03. Wed 19/08/2026 05:00 04. Thu 20/08/2026 05:00 05. Fri 21/08/2026 05:00 06. Sat 22/08/2026 05:00 | Civil: 01. Tue 18/08/2026 04:00 02. Wed 19/08/2026 04:00 03. Thu 20/08/2026 04:00 04. Fri 21/08/2026 04:00 05. Sat 22/08/2026 04:00 06. Sun 23/08/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00845 | Civil: 01. Mon 24/08/2026 05:00 02. Tue 25/08/2026 05:00 03. Wed 26/08/2026 05:00 04. Thu 27/08/2026 05:00 05. Fri 28/08/2026 05:00 06. Sat 29/08/2026 05:00 | Civil: 01. Tue 25/08/2026 04:00 02. Wed 26/08/2026 04:00 03. Thu 27/08/2026 04:00 04. Fri 28/08/2026 04:00 05. Sat 29/08/2026 04:00 06. Sun 30/08/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00846 | Civil: 01. Mon 31/08/2026 05:00 02. Tue 01/09/2026 05:00 03. Wed 02/09/2026 05:00 04. Thu 03/09/2026 05:00 05. Fri 04/09/2026 05:00 06. Sat 05/09/2026 05:00 | Civil: 01. Tue 01/09/2026 04:00 02. Wed 02/09/2026 04:00 03. Thu 03/09/2026 04:00 04. Fri 04/09/2026 04:00 05. Sat 05/09/2026 04:00 06. Sun 06/09/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00847 | Civil: 01. Mon 07/09/2026 05:00 02. Tue 08/09/2026 05:00 03. Wed 09/09/2026 05:00 04. Thu 10/09/2026 05:00 05. Fri 11/09/2026 05:00 06. Sat 12/09/2026 05:00 | Civil: 01. Tue 08/09/2026 04:00 02. Wed 09/09/2026 04:00 03. Thu 10/09/2026 04:00 04. Fri 11/09/2026 04:00 05. Sat 12/09/2026 04:00 06. Sun 13/09/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00848 | 06. Sat 19/09/2026 05:00 Civil: 01. Mon 14/09/2026 05:00 02. Tue 15/09/2026 05:00 03. Wed 16/09/2026 05:00 04. Thu 17/09/2026 05:00 05. Fri 18/09/2026 05:00 | 06. Sun 20/09/2026 04:00 Civil: 01. Tue 15/09/2026 04:00 02. Wed 16/09/2026 04:00 03. Thu 17/09/2026 04:00 04. Fri 18/09/2026 04:00 05. Sat 19/09/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00849 | Civil: 01. Mon 21/09/2026 05:00 02. Tue 22/09/2026 05:00 03. Wed 23/09/2026 05:00 04. Thu 24/09/2026 05:00 05. Fri 25/09/2026 05:00 06. Sat 26/09/2026 05:00 | Civil: 01. Tue 22/09/2026 04:00 02. Wed 23/09/2026 04:00 03. Thu 24/09/2026 04:00 04. Fri 25/09/2026 04:00 05. Sat 26/09/2026 04:00 06. Sun 27/09/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00850 | Civil: 01. Mon 28/09/2026 05:00 02. Tue 29/09/2026 05:00 03. Wed 30/09/2026 05:00 04. Thu 01/10/2026 05:00 05. Fri 02/10/2026 05:00 06. Sat 03/10/2026 05:00 | Civil: 01. Tue 29/09/2026 04:00 02. Wed 30/09/2026 04:00 03. Thu 01/10/2026 04:00 04. Fri 02/10/2026 04:00 05. Sat 03/10/2026 04:00 06. Sun 04/10/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00851 | Civil: 01. Mon 05/10/2026 05:00 02. Tue 06/10/2026 05:00 03. Wed 07/10/2026 05:00 04. Thu 08/10/2026 05:00 05. Fri 09/10/2026 05:00 06. Sat 10/10/2026 05:00 | Civil: 01. Tue 06/10/2026 04:00 02. Wed 07/10/2026 04:00 03. Thu 08/10/2026 04:00 04. Fri 09/10/2026 04:00 05. Sat 10/10/2026 04:00 06. Sun 11/10/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00852 | Civil: 01. Mon 12/10/2026 05:00 02. Tue 13/10/2026 05:00 03. Wed 14/10/2026 05:00 04. Thu 15/10/2026 05:00 05. Fri 16/10/2026 05:00 06. Sat 17/10/2026 05:00 | Civil: 01. Tue 13/10/2026 04:00 02. Wed 14/10/2026 04:00 03. Thu 15/10/2026 04:00 04. Fri 16/10/2026 04:00 05. Sat 17/10/2026 04:00 06. Sun 18/10/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00853 | Civil: 01. Mon 19/10/2026 05:00 02. Tue 20/10/2026 05:00 03. Wed 21/10/2026 05:00 04. Thu 22/10/2026 05:00 05. Fri 23/10/2026 05:00 06. Sat 24/10/2026 05:00 | Civil: 01. Tue 20/10/2026 04:00 02. Wed 21/10/2026 04:00 03. Thu 22/10/2026 04:00 04. Fri 23/10/2026 04:00 05. Sat 24/10/2026 04:00 06. Sun 25/10/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00854 | Civil: 01. Mon 26/10/2026 05:00 02. Tue 27/10/2026 05:00 03. Wed 28/10/2026 05:00 04. Thu 29/10/2026 05:00 05. Fri 30/10/2026 05:00 06. Sat 31/10/2026 05:00 | Civil: 01. Tue 27/10/2026 04:00 02. Wed 28/10/2026 04:00 03. Thu 29/10/2026 04:00 04. Fri 30/10/2026 04:00 05. Sat 31/10/2026 04:00 06. Sun 01/11/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00855 | Civil: 01. Mon 02/11/2026 05:00 02. Tue 03/11/2026 05:00 03. Sat 07/11/2026 05:00 | Civil: 01. Tue 03/11/2026 04:00 02. Wed 04/11/2026 04:00 03. Sun 08/11/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202505-00626 | Civil: 01. Wed 04/11/2026 07:30 | Civil: 01. Fri 06/11/2026 18:00 | General Mtce | TOTAL TRACK CLOSURE (REDLYNCH - KURANDA) TRAINS AFFECTED: TRAVEL | Townsville Track Possessions
PB202512-00856 | Civil: 01. Mon 09/11/2026 05:00 02. Tue 10/11/2026 05:00 03. Wed 11/11/2026 05:00 04. Thu 12/11/2026 05:00 05. Fri 13/11/2026 05:00 06. Sat 14/11/2026 05:00 | Civil: 01. Tue 10/11/2026 04:00 02. Wed 11/11/2026 04:00 03. Thu 12/11/2026 04:00 04. Fri 13/11/2026 04:00 05. Sat 14/11/2026 04:00 06. Sun 15/11/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00857 | Civil: 01. Mon 16/11/2026 05:00 02. Tue 17/11/2026 05:00 03. Wed 18/11/2026 05:00 04. Thu 19/11/2026 05:00 05. Fri 20/11/2026 05:00 06. Sat 21/11/2026 05:00 | Civil: 01. Tue 17/11/2026 04:00 02. Wed 18/11/2026 04:00 03. Thu 19/11/2026 04:00 04. Fri 20/11/2026 04:00 05. Sat 21/11/2026 04:00 06. Sun 22/11/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00858 | Civil: 01. Mon 23/11/2026 05:00 02. Tue 24/11/2026 05:00 03. Wed 25/11/2026 05:00 04. Thu 26/11/2026 05:00 05. Fri 27/11/2026 05:00 06. Sat 28/11/2026 05:00 | Civil: 01. Tue 24/11/2026 04:00 02. Wed 25/11/2026 04:00 03. Thu 26/11/2026 04:00 04. Fri 27/11/2026 04:00 05. Sat 28/11/2026 04:00 06. Sun 29/11/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00859 | Civil: 01. Mon 30/11/2026 05:00 02. Tue 01/12/2026 05:00 03. Wed 02/12/2026 05:00 04. Thu 03/12/2026 05:00 05. Fri 04/12/2026 05:00 06. Sat 05/12/2026 05:00 | Civil: 01. Tue 01/12/2026 04:00 02. Wed 02/12/2026 04:00 03. Thu 03/12/2026 04:00 04. Fri 04/12/2026 04:00 05. Sat 05/12/2026 04:00 06. Sun 06/12/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00860 | Civil: 01. Mon 07/12/2026 05:00 02. Tue 08/12/2026 05:00 03. Wed 09/12/2026 05:00 04. Thu 10/12/2026 05:00 05. Fri 11/12/2026 05:00 06. Sat 12/12/2026 05:00 | Civil: 01. Tue 08/12/2026 04:00 02. Wed 09/12/2026 04:00 03. Thu 10/12/2026 04:00 04. Fri 11/12/2026 04:00 05. Sat 12/12/2026 04:00 06. Sun 13/12/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00861 | Civil: 01. Mon 14/12/2026 05:00 02. Tue 15/12/2026 05:00 03. Wed 16/12/2026 05:00 04. Thu 17/12/2026 05:00 05. Fri 18/12/2026 05:00 06. Sat 19/12/2026 05:00 | Civil: 01. Tue 15/12/2026 04:00 02. Wed 16/12/2026 04:00 03. Thu 17/12/2026 04:00 04. Fri 18/12/2026 04:00 05. Sat 19/12/2026 04:00 06. Sun 20/12/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions
PB202512-00862 | 05. Fri 25/12/2026 05:00 06. Sat 26/12/2026 05:00 Civil: 01. Mon 21/12/2026 05:00 02. Tue 22/12/2026 05:00 03. Wed 23/12/2026 05:00 04. Thu 24/12/2026 05:00 | 05. Sat 26/12/2026 04:00 06. Sun 27/12/2026 04:00 Civil: 01. Tue 22/12/2026 04:00 02. Wed 23/12/2026 04:00 03. Thu 24/12/2026 04:00 04. Fri 25/12/2026 04:00 | Bridge Mtce | TOTAL TRACK CLOSURE - (CAMP OVEN - BARRON FALLS) SURPRISE CREEK AND CHRISTMAS CREEK PAINTING AND REPAIRS 0500 - 1100 - WORK BETWEEN TRAINS 1100 - 1300 - TOTAL TRACK CLOSURE 1300 - 1630 - WORK BETWEEN TRAINS 1630 - 0400 - TOTAL TRACK CLOSURE | Townsville Track Possessions